## Bug report
Bug ID | Description/Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot
BUG ID: DRBG5-61 | User is able to register an account by providing an invalid phone number | 1.Open the application URL 2.Goto signup page 3.Enter valid details into the fieldsdisplayed on the 'Sign Up' page 4.Enter invalid phone number like abcde1234@ into the 'phone number' field 5.Click on 'REGISTER' button | Should display a warning message "Invalid phone number" | Instead of error message there is a pop up message "New user added" | Major | P1(Medium)
BUG ID: DRBG5-43 | User is able to register an account by providing an existing email address | 1.Open the application URL 2.Goto signup page 3.Enter valid details into the fields displayed on the 'Sign Up' page 4.Enter an existing email address into the 'email' field 5.Click on 'REGISTER' button | Should display a warning message "Email address is already existing" | Instead of error message there is a pop up message "New user added" | Major | P1(Medium)
BUG ID: DRBG5-45 | Confirm password' field in 'Sign Up' page accepting wrong or incomplete password and, not showing warning message | 1.Open the application URL 2.Goto signup page 3.Enter valid details into the fields displayed on the 'Sign Up' page 4.Enter wrong or incomplete password into the 'Confirm password' field 5.Click on 'REGISTER' button | Should display a warning message like "It does not match to password" | User couldn't get any warning message | Major | P1(Medium)
BUG ID: DRBG5-17 | User is able to type the valid user nameand invalid password | 1.User should be able to type the valid user name and invalid pasword. 2.Click login | User should get an error message like 'user name and password do not match any user in this device' after typing the invalid password. | Error message is not displayed | Major | P1(Medium)
BUG ID: DRBG5-18 | User is able to type the invalid user name and valid password | 1.User should be able to type the invalid user name and valid pasword. 2.Click login | User should get an error message like 'user name and password do not match any user in this device' after typing the invalid username. | Error message is not displayed | Major | P1(Medium)
BUG ID: DRBG5-19 | User is able to type the invalid user name and invalid password | 1.User should be able to type the invalid user name and invalid pasword. 2.Click login | User should get an error message like 'user name and password do not match any user in this device' after typing the invalid username. | Error message is not displayed | Major | P1(Medium)
BUG ID: DRBG5-20 | User is able to type the valid user name and null password | 1.User should be able to type the user name 2.Click login | User should get an error message like 'please enter valid pasword' | Error message is not displayed | Major | P1(Medium)
BUG ID: DRBG5-58 | User is able to type the valid password and null username | 1.User should be able to type the password 2.Click login | User should get an error message like 'please enter valid username' | Error message is not displayed | Major | P1(Medium)
BUG ID - DRBG5-29 | Profile can't be created with a name having characters more than 20 | 1.User should be able to create profile using name having more than 20 characters | Profile should be created | No profle created | Major | P3(Medium)
BUG ID - DRBG5-23 | User can delete their resume by clicking on the delete button present on the keyboard | 1.OPEN WEBSITE 2.Click SignUp Now Button 3.Click Login 4.Click MY PROFILE button 5.Click Delete Profile button | User resume Deleted | Resume not Deleted | Major | P2(Medium)
BUG Id -DRBG5-24 | User can able to recover their deleted resume | 1.OPEN WEBSITE 2.Click SignUp Now Button 3.Click Login 4.Click MY PROFILE button 5.Click Delete Profile button | User resume recovered | No Option for recover | Major | P2(Medium)
BUG ID - DRBG5-25 | User can able to save downloaded file in desire location | 1.OPEN WEBSITE 2.Click SignUp Now Button 3.Click Login 4.Click MY PROFILE button 5.Click Download Resume button | Save resume in desire location | No Option for selecting desire location | Major | P2(Medium)
BUG ID - DRBG5-26 | User can cancel or stop downloading.their created resume | 1.OPEN WEBSITE 2.Click SignUp Now Button 3.Click Login 4.Click MY PROFILE button 5.Click Download Resume button | User cancel downloading | Cancel button is not present | Major | P2(Medium)
BUG ID - DRBG5-27 | A confirmation message popup or alert shown as the user clicks on the Send a Weblink button | 1.OPEN WEBSITE 2.Click SignUp Now Button 3.Click Login Button 4.Click MY PROFILE button 5.Click Send a weblink | Confirmation message is displayed | Confirmation message is not displayed | Major | P2(Medium)
BUG ID - DRBG5-28 | User can share weblink | 1.OPEN WEBSITE 2.Click SignUp Now Button 3.Enter Username And Password 4.Click Login Button 5.Click MY PROFILE button 6.Click Send a weblink | User can share | The browser is not supported message is displayed | Major | P2(Medium)
BUG ID - DRBG5-57 | no validation message came | 1. Open website link 2. Click login 3. Click my profile 4. Click edit details 5. Not entering values in mandatory fields | Profile should not be updated | Profile updated even without mandatory fields | Major | P4(Medium)